| APPENDIX 5 Provider | Project Name | Total Units | Larger | Ambulant | Wheelchair | Tenure | Total Grant | Grant Draw Down pre- 2027/28 | Projected Grant Draw Down 2027/28 | Projected Grant Draw Down 2028/29 | Projected Grant Draw Down 2029/30 | Projected Grant Draw Down 20230/31 | Projected Grant Draw Down 2031/32 | Future Years | Total points | 20 min neighbourhood |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Bield | Dean Court | 49 | 0 | 45 | 4 | SR | £6,370,000 | - | - | - | £1,500,000 | £2,000,000 | £3,370,000 | - | 1015 | Good |
| Cairn | Adam Grossert Court | 37 | 0 | 31 | 6 | SR | £1,961,000 | - | - | - | - | £1,000,000 | £961,000 | - | 910 | Excellent |
| Falkirk Council | Bowhouse | 9 | 2 | 0 | 0 | SR | £1,145,576 | - | - | £1,145,576 | - | - | - | - | 1050 | Good |
| Falkirk Council | Buy Backs 26-32* | 250 | 8 | 0 | 0 | SR | £15,750,000 | - | £3,150,000 | £3,150,000 | £3,150,000 | £3,150,000 | £3,150,000 | - | 900 | Good |
| Falkirk Council | Former Denny High* | 137 | 11 | 25 | 7 | SR | £12,579,000 | £8,488,000 | £2,591,000 | £1,500,000 | - | - | - | - | 1040 | Good |
| Falkirk Council | Former Larbert Nursery | 10 | 0 | 0 | 1 | SR | £1,257,776 | - | - | - | - | £1,257,776 | - | - | 900 | Good |
| Kingdom HA | Kilsyth Road, Banknock | 68 | 0 | 6 | 4 | SR, MMR & SE | £8,228,000 | - | - | - | - | - | £1,00,000 | £7,228,000 | 1040 | Good |
| Kingdom HA | Polmont | 12 | 2 | 2 | 0 | MMR & SE | £984,000 | - | - | - | £984,000 | - | - | - | 1105 | Moderate |
| Link (Curb) | Bellsdyke Road | 30 | 2 | 0 | 4 | SR | £3,960,000 | - | - | - | - | £2,000,000 | £1,960,000 | - | 810 | Moderate |
| Link (Curb) | Crawfield Road (B) | 34 | 3 | 0 | 6 | SR | £4,552,375 | £1,000,000 | £3,552.375 | - | - | - | - | - | 990 | Moderate |
| Link (Curb) | My Dub Ph2 | 34 | 2 | 0 | 4 | SR | £4,609,304 | £500,000 | £2,000,000 | £2,109,305 | - | - | - | - | 965 | Moderate |
| Paragon | Buy Back 27-32 | 25 | 5 | 0 | 0 | SR | £1,725,000 | - | £345,000 | £345,000 | £345,000 | £345,000 | £345,000 | - | 900 | Good |
| Paragon | Old Salvation Army Hall | 38 | 0 | 0 | 4 | SR | £5,222,000 | - | - | - | - | £3,000,000 | £2,222,000 | - | 965 | Excellent |
| Wheatley/Loretto | Carron Road | 82 | 10 | 30 | 4 | SR & MMR | £9,503,479 | £3,000,000 | £3,000,000 | £3,503,479 | - | - | - | - | 1040 | excellent |
| Wheatley/Loretto | Crawfield Road (L) | 40 | 2 | 0 | 2 | SR | £5,703,000 | - | - | £3,000,000 | £2,730,000 | - | - | - | 965 | moderate |
| Wheatley/Loretto | Dennyloanhead Ph1 | 41 | 2 | 0 | 2 | SR | £5,080,000 | - | £1,000,000 | £2,080,000 | £2,000,000 | - | - | - | 1390 | moderate |
| Wheatley/Loretto | Dennyloanhead Ph2 | 43 | 6 | 0 | 2 | SR | £5,752,000 | - | - | - | - | - | £3,000,000 | £2,752,000 | 1390 | moderate |
| Wheatley/Loretto | Gilston, Polmont (TW) | 39 | 0 | 0 | 4 | SR | £4,800,000 | £3,000,000 | £1,800,000 | - | - | - | - | - | 1105 | Poor |
| Wheatley/Loretto | Gilston, Polmont Ph1 | 85 | 4 | 0 | 9 | SR | £10,943,062 | - | - | - | £4,940,000 | £6,000,000 | - | - | 980 | Poor |
| Wheatley/Loretto | Gilston, Polmont Ph2 | 35 | 9 | 0 | 1 | MMR | £3,702,725 | - | - | - | - | £500,000 | £3,202,725 | - | 1030 | Poor |
| Wheatley/Loretto | Vellore Road Ph2 | 34 | 0 | 0 | 4 | SR | £4,794,000 | - | - | - | - | £2,000,000 | £2,794,000 | - | 780 | Moderate |
| Wheatley/Loretto | Wellpark Road | 12 | 0 | 0 | 2 | SR | £1,595,000 | - | - | £505,000 | £1,000,000 | - | - | - | 1340 | Moderate |
| Wheatley/Loretto | Whitecross | 56 | 4 | 4 | 2 | SR & MMR | £7,279,000 | - | £3,297,000 | £3,000,000 | £1,000,000 | - | - | - | 1280 | moderate |
| Total |  | 1200 | 72 | 733 | 181 | 72 |  | £127,496,297 | £15,488,000 | £19,217,305 | £20,319,055 | £21,353,766 | £22,004,725 | £9,980,000 |  |  |

| Shadow Programme 2027-2032 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Provider | Project Name | Total Units | Larger (4+) | ambulant | Wheel-chair | Tenure | Total Grant | Grant Spend pre-27/28 | Projected Grant Draw Down 27/28 |  | Projected Grant Draw Down 28/29 | Projected Grant Draw Down 29/30 | Projected Grant Draw Down 30/31 | Projected Grant Draw Down 31/32 | Future Years | Total Points | 20 minute neighbour -hood |
| Falkirk Council | Seabegs Road | 31 | 2 | 2 | 2 | SR | £3,854,720 | - | - |  | - | - | - | - | - | 715 | Good |
| Falkirk Council | Banknock South | 101 | 4 | 24 | 9 | SR | £11,524,772 | - | - |  | - | - | - | - | - | 1215 | Moderate |
| Falkirk Council | King Street | 21 | 0 | 17 | 4 | SR | £2,333,714 | - | - |  | - | - | - | - | - | 1135 | Excellent |
| Falkirk Council | Kerse Road | 10 | 0 | 10 | 0 | SR | £1,030,892 | - | - |  | - | - | - | - | - | 1100 | Excellent |
| Link (Curb) | Station Road | 23 | 2 | 0 | 2 | SR | £2,875,000 | - | - |  | - | - | - | - | - | 730 | Moderate |
| Total |  | 186 | 8 | 43 | 17 |  | £21,619,098 | - | - |  | - | - | - | - | - |  |  |