Timeline for events

| 6 months before the event | - Notification to Falkirk Council of planned major public event including location, dates, duration and capacity. - Land/Venue booking to be made. |
| --- | --- |
| 4 months before the event. | - Submission of application for public entertainment licence. - Submission of draft event manual including emergency procedures and stewarding expectations. - Submission of detailed site plans, including position of main event arena, access/egress points, temporary structures and on-site facilities. - Submission of draft stewarding/security plan. - Submission of draft medical management plan. - Submission of draft traffic management plan. - Submission of emergency plan and evacuation plan. - Submission of site-specific risk assessments and fire risk assessments, including details of any LPG usage. - Details of any stalls, water points and litter picking plans. - Details of emergency access. - Details of primary contacts who will be responsible for ensuring all event plans are adhered to. - Details of any parking requirements. |
| 3 months before event. | - Applications for alcohol licences to be made (note – no Board in July). - Submission of alcohol plan. - Application for temporary traffic regulation order. - Application for section 89 |
| 2 months before the event | - Submission of all trader names to Environmental Health. - Attend first safety advisory group. |
| 1 month before the event | - Attend licensing board if event is selling alcohol and the attendance is estimated to be over 1000. - Attend second safety advisory group. |
| 21 days before the event | - If not already completed all final paperwork to be submitted. |
| 1 day before event | - Possible site visit. - Sound checks to be carried out in conjunction with representatives of the environmental health department. - Stage checks to be completed by building standards |
| 1-5 days after event | - Site check in line with land lease terms and conditions. |