## SHIP Table
|  |  | Units – tenure Units – Built Form Unit – Type | Units – tenure Units – Built Form Unit – Type | Units – tenure Units – Built Form Unit – Type | Units – tenure Units – Built Form Unit – Type | Units – tenure Units – Built Form Unit – Type | Units – tenure Units – Built Form Unit – Type | Units – tenure Units – Built Form Unit – Type | Units – tenure Units – Built Form Unit – Type | Units – tenure Units – Built Form Unit – Type | Units – tenure Units – Built Form Unit – Type | Units – tenure Units – Built Form Unit – Type | Greener Standard | Site Start Date | Unit site start (over SHIP period) | Unit site start (over SHIP period) | Unit site start (over SHIP period) | Unit site start (over SHIP period) | Unit site start (over SHIP period) | Unit site start (over SHIP period) | Unit Site Completion (over SHIP period) | Unit Site Completion (over SHIP period) | Unit Site Completion (over SHIP period) | Unit Site Completion (over SHIP period) | Unit Site Completion (over SHIP period) | Unit Site Completion (over SHIP period) | Funding Required (million) | Funding Required (million) | Funding Required (million) | Funding Required (million) | Funding Required (million) | Funding Required (million) | Funding (over SHIP) (millions) | Funding (over SHIP) (millions)
Project | Area | Developer | SR | MMR | SE | Total | Rehab | Off shelf | NB | Total | GN | Specialist (ambulant or Wheelchair) | Total | Greener Standard | Site Start Date | 27/28 | 28/29 | 29/30 | 30/31 | 31/32 | Total | 27/28 | 28/29 | 29/30 | 30/31 | 31/32 | Total | Pre 26/27 | 27/28 | 28/29 | 29/30 | 30/31 | 31/32 | Total AHSP | Commuted Sums
Buy Backs | All | Paragon | 25 |  |  | 25 |  | 25 |  | 25 | 25 |  | 25 | N |  | 5 | 5 | 5 | 5 | 5 | 25 | 5 | 5 | 5 | 5 | 5 | 25 |  | 345,000 | 345,000 | 345,000 | 345,000 | 345,000 | £1,725,000
Buy Backs | All | Falkirk Council | 250 |  |  | 250 |  | 250 |  | 250 | 250 |  | 250 | N |  | 50 | 50 | 50 | 50 | 50 | 250 | 50 | 50 | 50 | 50 | 50 | 250 |  | 3,150,000 | 3,150,000 | 3,150,000 | 3,150,000 | 3,150,000 | £15,750,000
Old Salvation Army Hall | Larbert & Rural North | Paragon | 38 |  |  | 38 |  |  | 38 | 38 | 34 | 4 | 38 | Y | Mar-29 |  |  | 20 | 18 |  | 38 |  |  |  | 20 | 18 | 38 | 30/31: 3,000,000; 31/32: 2,222,000 | £5,222,000
Adam Grossart Court | Larbert & Rural North | Cairn Housing Association | 37 |  |  | 37 | 37 |  |  | 37 |  | 37 | 37 | Y | Apr-28 |  | 37 |  |  |  | 37 |  |  |  | 37 |  | 37 | 30/31: 1,000,000; 31/32: 961,000 | £1,961,000
Dean Court | Bo'ness | Bield Housing & Care | 49 |  |  | 49 |  |  | 49 | 49 |  | 49 | 49 | Y | May-27 | 49 |  |  |  |  | 49 |  |  | 49 |  |  | 49 | 29/30: 1,500,000; 30/31: 2,000,000; 31/32: 2,870,000 | £6,370,000
Crawfield Road (Bancon) | Bo'ness | Link Group | 34 |  |  | 34 |  |  | 34 | 34 | 28 | 6 | 34 | Y | Oct-26 | 34 | [5 empty] | 34 |  |  |  |  | 34 | Pre 26/27: 1,000,000; 27/28: 3,552,376 | £4,552,376
Bellsdyke Road | Larbert & Rural North | Link Group | 30 |  |  | 30 |  |  | 30 | 30 | 26 | 4 | 30 | Y | Jul-27 | 30 |  |  |  |  | 30 |  |  | 30 |  |  | 30 | 30/31: 2,000,000; 31/32: 1,960,000 | £3,960,000
MyDub2 | Bonnybridge/Denny | Link Group | 34 |  |  | 34 |  |  | 34 | 34 | 30 | 4 | 34 | Y | Jul-27 | 20 | 14 |  |  |  | 34 |  |  | 34 |  |  | 34 | 27/28: 500,000; 28/29: 2,000,000; 29/30: 2,109,305 | £4,609,304
Dennyloanhead Ph1 | Bonnybridge/Denny | Wheatley/Loretto | 41 |  |  | 41 |  |  | 41 | 41 | 39 | 2 | 39 | Y | Jul-27 | 31 | 10 |  |  |  | 41 |  | 31 | 10 |  |  | 41 | 27/28: 1,000,000; 28/29: 2,080,000; 29/30: 2,000,000 | £5,080,000
Dennyloanhead Ph2 | Bonnybridge/Denny | Wheatley/Loretto | 43 |  |  | 43 |  |  | 43 | 43 | 41 | 2 | 41 | Y | Aug-31 |  |  |  | 10 | 20 | 30 |  |  |  |  | 21 | 21 | 31/32: 3,000,000 | £3,000,000
Gilston (Taylor Wimpey) | Braes and Rural South | Wheatley/Loretto | 39 |  |  | 39 |  |  | 39 | 39 | 35 | 4 | 35 | Y | Oct-26 | [5 empty] | 0 | 39 |  |  |  |  | 39 | Pre 26/27: 3,000,000; 27/28: 1,800,000 | £1,800,000
Gilston Farm Ph1 | Braes and Rural South | Wheatley/Loretto | 85 |  |  | 85 |  |  | 85 | 85 | 38 | 47 | 38 | Y | Apr-27 | 31 | 32 | 22 |  |  | 85 | 25 | 40 | 20 |  |  | 85 | 29/30: 4,940,000; 30/31: 6,000,000 | £10,940,000
Gilston Farm Ph2 | Braes and Rural South | Wheatley/Loretto |  | 35 |  | 35 |  |  | 35 | 35 | 35 |  | 35 | Y | Apr-30 |  | 20 | 25 |  |  | 35 |  |  | 20 | 15 |  | 35 | 30/31: 500,000; 31/32: 3,202,725 | £3,702,725
Carron Road | Falkirk | Wheatley/Loretto | 66 | 16 |  | 82 |  |  | 82 | 82 | 48 | 34 | 48 | Y | Jul-26 | 50 |  |  |  |  | 50 | 32 | 50 |  |  |  | 82 | Pre 26/27: 3,000,000; 27/28: 3,000,000; 28/29: 3,503,479 | £6,503,479
Whitecross | Braes and Rural South | Wheatley/Loretto | 44 | 12 |  | 56 |  |  | 56 | 56 | 50 | 6 | 50 | Y | Jan-27 | 29 |  |  |  |  | 29 | 27 | 29 |  |  |  | 56 | 27/28: 3,279,000; 28/29: 3,000,000; 29/30: 1,000,000 | £7,279,000
Crawfield Road (lovell) | Bo'ness | Wheatley/Loretto | 40 |  |  | 40 |  |  | 40 | 40 | 38 | 2 | 38 | Y | Oct-27 | 40 |  |  |  |  | 40 |  | 40 |  |  |  | 40 | 28/29: 3,000,000; 29/30: 2,703,000 | £5,703,000
Wellpark Road | Bonnybridge/Denny | Wheatley/Loretto | 12 |  |  | 12 |  |  | 12 | 12 | 10 | 2 | 10 | Y | Sep-27 | 12 |  |  |  |  | 12 |  | 12 |  |  |  | 12 | 28/29: 595,000; 29/30: 1,000,000 | £1,595,000
Vellore Road | Braes and Rural South | Wheatley/Loretto | 34 |  |  | 34 |  |  | 34 | 34 | 30 | 4 | 30 | Y | Oct-27 | 14 | 20 |  |  |  | 34 |  | 14 | 20 |  |  | 34 | 30/31: 2,000,000; 31/32: 2,794,000 | £4,794,000
Kilsyth Road, Banknock | Bonnybridge/Denny | Kingdom Housing Association | 30 | 24 | 14 | 68 |  |  | 68 | 68 | 28 | 10 | 68 | Y | Apr-29 |  |  |  |  | 20 | 20 | [5 empty] | 0 | 30/31: 1,000,000; 31/32: 7,228,000 | £1,000,000
Polmont Park | Braes and Rural South | Kingdom Housing Association |  | 6 | 6 | 12 |  |  | 12 | 12 | 12 |  | 12 | Y | Jan-28 | 12 |  |  |  |  | 12 |  | 12 |  |  |  | 12 | 29/30: 984,000 | £948,000
Bowhouse | Grangemouth | Falkirk Council | 9 |  |  | 9 |  |  | 9 | 9 | 9 |  | 9 | Y | Feb-28 |  | 9 |  |  |  | 9 |  |  | 9 |  |  | 9 | 28/29: 1,145,576 | £1,145,576
Former Denny High School | Bonnybridge/Denny | Falkirk Council | 137 |  |  | 137 |  |  | 137 | 137 | 105 | 32 | 137 | Y | Dec-25 | 137 |  |  |  |  | 137 | 37 | 100 |  |  |  | 137 | Pre 26/27: 8,488,000; 27/28: 2,591,000; 28/29: 1,500,000 | £4,091,000
Former Larbert Day Nursery | Larbert & Rural North | Falkirk Council | 10 |  |  | 10 |  |  | 10 | 10 | 9 | 1 | 10 | Y | Apr-29 |  |  |  | 10 |  | 10 |  |  |  | 10 |  | 10 | 30/31: 1,257,776 | £1,257,776
Seabegs Road, Bonnybridge | Bonnybridge/Denny | Falkirk Council | 31 |  |  | 31 |  |  | 31 | 31 | 27 | 4 | 31 | Y
Banknock South | Bonnybridge/Denny | Falkirk Council | 101 |  |  | 101 |  |  | 101 | 101 | 80 | 21 | 101 | Y
King Street | Larbert & Rural North | Falkirk Council | 21 |  |  | 21 |  |  | 21 | 21 |  | 21 | 21 | Y
Kerse Road | Grangemouth | Falkirk Council | 10 |  |  | 10 |  |  | 10 | 10 |  | 10 | 10 | Y
Station Road | Braes and Rural North | Link (Curb) | 23 |  |  | 23 |  |  | 23 | 23 | 21 | 2 | 23 | Y
HIF Sites
Shadow Programme