## Sheet1
Housing Land Audit 2025/26 - summary all sites | [11 empty] | Short Term |  |  | Medium Term |  |  | Long Term
Site Ref | LDP2 | Status | Developer Type | Site Name | Settlement | Company Name | Complete 31/3/25 | Under construction | Remainder | Total under construction and remainder | Non contributing/constrained | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035+ | Permission Status | Disputed | Deliverability Status | Action Required
Bo'ness
555 | H06 | HLA | Housing Assoc. | Union Street | Bo'ness | Link HA | 0 | 30 | 0 | 30 |  | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP/detailed |  | Deliverable
665 |  | HLA | Landowner | Bridgeness Road 3 | Bo'ness | Mr M Sroka | 0 | 0 | 6 | 6 |  | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed |  | Deliverable
695 | MU02 | HLA | Private Dev. | Drum Farm South | Bo'ness | Miller Homes | 19 | 51 | 145 | 196 |  | 69 | 63 | 50 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP/detailed |  | Deliverable
813 | H55 | HLA | Private Dev. | Crawfield Road Phase 2 | Bo'ness | Cala | 0 | 0 | 226 | 226 |  | 0 | 10 | 36 | 36 | 36 | 36 | 36 | 36 | 0 | 0 | 0 | LDP/detailed |  | Deliverable
813 | H56 | HLA | Private Dev. | Crawfield Road Phase 1 | Bo'ness | Robertson | 0 | 0 | 227 | 227 |  | 21 | 26 | 43 | 43 | 26 | 26 | 26 | 16 |  |  |  | LDP/detailed |  | Deliverable
842 | H56 | HLA | Private Dev. | North Bank Farm | Bo'ness | Miller Homes/Persimmon | 102 | 8 | 68 | 76 |  | 17 | 36 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP/detailed |  | Deliverable
903 |  | HLA | Landowner | Northbank Farm Holding | Bo'ness | Northbank Farm Holding | 0 | 0 | 11 | 11 |  | 0 | 0 | 1 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | detailed |  | Deliverable
390 | H01 | HLA | Private Dev. | Drum Farm North | Bo'ness | Ogilvie Homes | 105 | 0 | 90 | 90 |  | 0 | 0 | 0 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | LDP/det |  | Deliverable with Constraints | Detailed planning consent required
63 | H05 | Non Contributing HLA | Landowner | Main Street A | Bo'ness | Unknown | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Deliverable with Constraints | No specific actions identified
868 | MU03 | Non Contributing HLA | Landowner | Crawfield Lane | Bo'ness | Unknown | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Deliverable with Constraints | Identify landowner and developer intentions
867 | MU01 | Non Contributing HLA | Landowner | Links Road | Bo'ness | Unknown | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Undeliverable | Not being promoted. Multiple ownerships, no specific actions identified. Site is unlikely to be able to address flood risk.
175 | H03 | Non Contributing HLA | Landowner | Kinglass Farm 2 | Bo'ness | Mr Robert Kirk | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Undeliverable | Access is not achievable without third party land
646 | H04 | Non Contributing HLA | Landowner | South Street | Bo'ness | H & K Estates Ltd | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Deliverable with Constraints | Housebuilder to be attached. Pipeline restrictions to be addressed.
Bonnybridge and Banknock
437 | MU04 | HLA | Private Dev. | Banknock North | Banknock | Persimmon Homes North Scotland | 0 | 0 | 453 | 453 |  | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 103 | LDP/outline |  | Deliverable with Constraints | Planning consent to be issued
274 | H11 | HLA | Local Auth. | Seabegs Road | Bonnybridge | Falkirk Council | 0 | 0 | 31 | 31 |  | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | LDP | disputed | Deliverable with Constraints | Planning application from Council, SHIP funding to be confirmed
897 |  | Non Contributing HLA | Landowner | Glen Etive, Kilsyth Road | Haggs | Unknown | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | outline |  | Undeliverable
869 | H53 | HLA | Landowner | Cumbernauld Road | Longcroft | Mr D Gallacher | 0 | 0 | 4 | 4 |  | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP/detailed |  | Deliverable
578 | MU05 | HLA | Landowner | Bonnybridge Town Centre | Bonnybridge | Unknown | 0 | 0 | 5 | 5 |  | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP/detailed |  | Deliverable with Constraints | New planning application to be to be approved
436 | H08 | HLA | Local Auth. | Banknock South | Banknock | Falkirk Council | 0 | 0 | 106 | 106 |  | 0 | 0 | 0 | 0 | 0 | 26 | 37 | 43 | 0 | 0 | 0 | LDP/detailed | disputed | Deliverable with Constraints | SHIP funding to be confirmed.
327 | H12 | HLA | Landowner | Garngrew Road | Banknock | Hamilton Brown Developments | 0 | 0 | 19 | 19 |  | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | LDP |  | Deliverable with Constraints | S75 to be signed
80/176 | H08 | HLA | Private Dev. | Bankock South (Bankier Distillery/Wellpark Road) | Banknock | Muir Homes Ltd | 0 | 0 | 78 | 78 |  | 0 | 0 | 0 | 35 | 35 | 8 | 0 | 0 | 0 | 0 | 0 | LDP |  | Deliverable | planning consent to be issued
348 | H09 | HLA | Private Dev. | Dennyloanhead | Dennyloanhead | Persimmon Homes East Scotland | 0 | 0 | 562 | 562 |  | 0 | 55 | 61 | 50 | 40 | 40 | 50 | 62 | 51 | 40 | 113 | LDP/detailed |  | Deliverable
862 |  | Non Contributing HLA | Landowner | 30-32 High Street | Bonnybridge | Unknown | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed |  | Constrained | Conversion works to be completed
491 | MU20 | HLA | Private Dev. | East Bonnybridge | Bonnybridge | Lochay Homes Ltd | 0 | 0 | 30 | 30 |  | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP | disputed | Deliverable with Constraints | Planning application to be approved
565 |  | Non Contributing HLA | Private Dev. | Bridge Street | Bonnybridge | Antonine Property Developments Group Ltd | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed |  | Deliverable with Constraints | planning consent to be implemented or revised application to be made
597 | H10 | Non Contributing HLA | Private Dev. | Broomhill Road | High Bonnybridge | Manor Forrest | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Deliverable with Constraints | Planning application to be submitted
638 |  | Non Contributing HLA | Landowner | Garngrew Road North | Haggs | Mr A Brown | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | outline |  | Undeliverable
Braes Urban Area
847 | H18 | HLA | Private Dev. | Parkhall Farm 5 | Maddiston | Ecosse Regeneration | 0 | 0 | 70 | 70 |  | 0 | 0 | 0 | 10 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | outline |  | Deliverable with Constraints | Planning application to be submitted. Housebuilder to be confirmed.
898 |  | HLA | Landowner | Greenpark Drive | Polmont | Unknown | 5 | 1 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed |  | Deliverable
874 | H20 | HLA | Private Dev. | Redding Park 2 | Reddingmuirhead | Gracey Ltd | 0 | 2 | 38 | 40 |  | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP/det |  | Deliverable
531 | H57 | HLA | Private Dev. | Maddiston Fire Station | Maddiston | Miller M2 Developments | 95 | 1 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP/outline |  | Deliverable
246 | MU06 | HLA | Private Dev. | Gilston | Polmont | Cala | 0 | 0 | 345 | 345 |  | 3 | 48 | 72 | 74 | 73 | 75 | 0 | 0 | 0 | 0 | 0 | LDP/detailed |  | Deliverable
246 | MU06 | HLA | Private Dev. | Gilston 2 | Polmont | Taylor Wimpey | 0 | 0 | 155 | 155 |  | Short Term 2025/26: 0; Short Term 2026/27: 30; Short Term 2027/28: 35; Medium Term 2028/29: 35; Medium Term 2029/30: 35; Medium Term 2030/31: 20
619 |  | HLA | Housing Assoc. | Westquarter Avenue | Westquarter | Link Group | 0 | 0 | 17 | 17 |  | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed |  | Deliverable
234 | H17 | Non Contributing HLA | Landowner | Toravon Farm | Maddiston | Unknown | 0 | 0 | 0 | 0 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Deliverable with Constraints | Planning application to be submitted. Housebuilder to be confirmed.
724 | H54 | Non Contributing HLA | Landowner | The Haining | Maddiston | Ion Care And Support Services | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Deliverable with Constraints | MSC planning application to be submitted. Housebuilder to be confirmed.
746 | H13 | Non Contributing HLA | Private Dev. | Parkhall Farm 1 | Maddiston | Manor Forrest | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Deliverable with Constraints | Planning application to be submitted. Housebuilder to be confirmed.
877 | H15 | Non Contributing HLA | Private Dev. | Parkhall Farm 3 | Maddiston | Lochay Homes Ltd | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Deliverable with Constraints | Multiple ownerships and flood risk to be addressed.
Denny
697 | H32 | HLA | Private Dev. | Mydub 2 | Denny | Avant Homes | 0 | 0 | 244 | 244 |  | 0 | 20 | 50 | 84 | 50 | 40 | 0 | 0 | 0 | 0 | 0 | LDP |  | Deliverable | Planning application to be approved
825 | H59 | HLA | Private Dev. | Rosebank North | Dunipace | Ogilvie Homes | 0 | 0 | 130 | 130 |  | 28 | 34 | 25 | 25 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | LDP/detailed |  | Deliverable | Phase 3 application to be submitted.
669 |  | HLA | Landowner | Annet Road | Head Of Muir | Mr N Khan | 3 | 1 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed |  | Deliverable
579 | H33 | HLA | Private Dev. | Carrongrove Mill | Stoneywood | Mactaggart/Mickel | 83 | 0 | 123 | 123 |  | 0 | 0 | 25 | 25 | 25 | 25 | 23 | 0 | 0 | 0 | 0 | LDP/det |  | Deliverable | S75 to be amended
503 | MU09 | HLA | Private Dev. | Broad Street | Denny | Cruden Homes (East) | 0 | 0 | 224 | 224 |  | 0 | 0 | 37 | 46 | 67 | 36 | 29 | 9 | 0 | 0 | 0 | LDP |  | Deliverable | Planning application to be approved
426 | H30 | HLA | Local Auth. | Former Denny High School (Phase 1) | Denny | Falkirk Council | 0 | 0 | 137 | 137 |  | 0 | 0 | 37 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP/detailed |  | Deliverable
| H30 | HLA | Private Dev. | Former Denny High School (Phase 2) | Denny | Unknown | 0 | 0 | 63 | 63 |  | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | LDP | disputed | Deliverable with Constraints | Site to be marketed. Housebuilder to be attached. Planning consent required.
870 | MU10 | Non Contributing HLA | Local Auth. | Church Walk | Denny | Falkirk Council | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Constrained | No actions identified
Falkirk
799 |  | Non Contributing HLA | Landowner | 1 Carradale Avenue | Tamfourhill | Unknown | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed |  | Deliverable with Constraints | Housebuilder to be attached. Planning application to be made.
250 | MU11 | Non Contributing HLA | Local Auth. | Portdownie | Camelon | Falkirk Council | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Constrained | Site remediation. Development partner required.
316 |  | HLA | Private Dev. | Glenochil Road | Falkirk | Mixed | 2 | 1 | 1 | 2 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed |  | Deliverable | Application to be made for final plot
383 | H43 | HLA | Landowner | Westburn Avenue | Falkirk | Forth Valley Health Board | 0 | 0 | 100 | 100 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | LDP |  | Deliverable with Constraints | Site masterplan required. Site to be marketed.
509 |  | HLA | Private Dev. | Seaforth Road | Bainsford | Roubaix Developments Ltd | 0 | 0 | 9 | 9 |  | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | none |  | Deliverable | Planning consent to be implemented
585 | MU16 | HLA | Landowner | Falkirk Gateway | Falkirk | Hargreaves Land Ltd | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | LDP |  | Deliverable with Constraints | Developable area to be confirmed by FRA. Alignment with wider masterplan for site to be confirmed. Housebuild required to be attached to site.
610 |  | HLA | Private Dev. | Maggie Woods Loan | Falkirk | Casa Homes (Scotland) Ltd | 8 | 4 | 0 | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed |  | Deliverable
704 | H42 | HLA | Local Auth. | Woodend Farm | Hallglen | Falkirk Council | 32 | 79 | 0 | 79 |  | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP/detailed |  | Deliverable
705 | H39 | HLA | Landowner | Cauldhame Farm | Falkirk | Mr G Steel/Elma Steel | 0 | 0 | 200 | 200 |  | 0 | 0 | 0 | 0 | 20 | 55 | 55 | 45 | 25 | 0 | 0 | LDP |  | Deliverable with Constraints | Housebuilder to be confirmed. Planning aplication to be submitted.
801 | MU17 | HLA | Housing Assoc. | Carron Road | Falkirk | Wheatley Group | 0 | 0 | 82 | 82 |  | 0 | 0 | 44 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Deliverable | S75 to be signed
863 |  | HLA | Landowner | Bean Row | Falkirk | Vkrr Investments Ltd | 4 | 0 | 1 | 1 |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed |  | Deliverable
889 |  | HLA | Private Dev. | 150 High Street | Falkirk | Hannigan Hotels Ltd | 0 | 0 | 7 | 7 |  | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed |  | Deliverable with Constraints | Planning consent to be implemented
908 |  | HLA | Private Dev. | Alma Street East | Falkirk | DNG Property Services Ltd | 0 | 0 | 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed |  | Deliverable | Planning consent to be implemented
901 |  | HLA | Private Dev. | Bankside | Bankside | McMillan Property Developments Ltd | 1 | 4 | 0 | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed |  | Deliverable
904 |  | Non Contributing HLA | Landowner | Canal Street | Falkirk | Unknown | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed |  | Deliverable with Constraints | Planning consent to be implemented
722 | H41 | Non Contributing HLA | Private Dev. | Grangemouth Road | Falkirk | Gannet Developments Ltd | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Undeliverable | No actions identified
501 | H44 | Non Contributing HLA | Landowner | Firs Park | Falkirk | Mr A Mackin | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Constrained | Access to be resolved, potential for third party land to be required.
872 | MU12 | Non Contributing HLA | Landowner | Grahamston | Falkirk | Unknown | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Constrained | no actions identified
888 |  | Non Contributing HLA | Private Dev. | Erskine Church, Hodge Street | Falkirk | Erskine Community Halls Ltd | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed extant |  | Deliverable with Constraints | Viability to be confirmed
612 | MU14 | Non Contributing HLA | Private Dev. | Bank Street | Falkirk | J R Johnston Development Ltd | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Constrained | Site to be marketed, housebuilder to be confirmed
562 | H36 | Non Contributing HLA | Landowner | Gowan Lane | Grahamston | Mr M Thompson (Nu-Car Auto Salvage Ltd) | 0 | 0 | 0 | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Constrained | Site to be marketed. Access to be resolved, potenial for wider development linked to adjacent sites
899 |  | Non Contributing HLA | Landowner | Thornhill Road | Falkirk | Unknown | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed |  | Undeliverable | No actions identified
563 | MU13 | Non Contributing HLA | Landowner | Callendar Riggs | Falkirk | Unknown | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Constrained | No actions identified
Grangemouth
871 | MU18 | Non Contributing HLA | Local Auth. | Grangemouth Town Centre | Grangemouth | Falkirk Council | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Constrained | Flood risk and major hazards to be addressed.
909 |  | HLA | Landowner | West of Thistle Avenue | Grangemouth | Unknown | 0 | 0 | 5 | 5 |  | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | outline |  | Deliverable with Constraints | Site being marketed, housebuilder to be confirmed. Planning application to be submitted
875 | MU21 | Non Contributing HLA | Local Auth. | Glensburgh | Grangemouth | Falkirk Council | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Undeliverable | No actions identified
Larbert and Stenhousemuir
885 | MU19 | HLA | Private Dev. | Hill Of Kinnaird 2 | Larbert | Cala/Persimmon | 0 | 0 | 70 | 70 |  | 0 | 0 | 30 | 30 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Deliverable | Planning application to be submitted
902 |  | HLA | Private Dev. | Bothkennar Road | Carronshore | Tollbooth Property Ltd | 11 | 4 | 0 | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed |  | Deliverable
906 |  | HLA | Private Dev. | Stirling Road West | Larbert | Heritage Homes Ltd | 0 | 0 | 6 | 6 |  | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed |  | Deliverable | Planning consent to be implemented
833 | H60 | HLA | Private Dev. | Stirling Road | Larbert | Avant Homes | 94 | 2 | 0 | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP/detailed |  | Deliverable
Rural North
315 |  | HLA | Landowner | Denovan Mains Farm | Denny | Mr D Graham | 3 | 0 | 4 | 4 |  | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed |  | Deliverable with Constraints | Site to be sold. Planning consent to be implemented.
334 | H52 | HLA | Private Dev. | Mclaren Park | Torwood | Heritage Homes Ltd | 8 | 3 | 0 | 3 |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP/det |  | Deliverable
355 | H48 | HLA | Private Dev. | Castle View | Airth | Lochay Homes Ltd | 68 | 27 | 0 | 27 |  | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP/detailed |  | Deliverable
798 |  | HLA | Landowner | Braeface Road 1 | Banknock | Unknown | 5 | 1 | 3 | 4 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed |  | Deliverable | Plots to be sold and plot planning application submitted.
850 |  | HLA | Private Dev. | Burnhouse Farm | Dunipace | Rustic Eco Properties | 5 | 1 | 4 | 5 |  | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed |  | Deliverable | Plots to be sold and plot planning application submitted.
886 |  | HLA | Private Dev. | Moss Road | Dunmore | Mixed | 0 | 0 | 10 | 10 |  | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | outline/detailed |  | Deliverable | Plots to be sold and plot planning application submitted.
890 |  | HLA | Private Dev. | South Bellsdyke Farm | Brackenlees | Rewd Group | 0 | 0 | 7 | 7 |  | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | detailed |  | Deliverable
326 | H49 | Non Contributing HLA | Private Dev. | Airth Castle South | Airth | Stewart Homes (Scotland) Ltd | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Deliverable with Constraints | Site to be marketed, housebuilder to be confirmed. Planning application to be submitted.
258 |  | Non Contributing HLA | Landowner | Dunmore House | Dunmore | Mrs Sutherland | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | outline extant |  | Undeliverable
333 | H50 | HLA | Landowner | The Glebe | Airth | Church Of Scotland General Trustees | 0 | 0 | 40 | 40 |  | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | LDP |  | Deliverable with Constraints | Site to be marketed, housebuilder to be confirmed, planning application submitted.
685 | H48 | Non Contributing HLA | Private Dev. | Castle View 1 | Airth | Mr P Mulholland | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP/detailed extant |  | Deliverable with Constraints | Housebuilder to be confirmed. Planning application submitted if original consent not developed.
Rural South
884 |  | HLA | Private Dev. | Hillcrest Plots | Shieldhill | Mixed | 3 | 1 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | outline/detailed |  | Deliverable
900 |  | HLA | Private Dev. | Avondale House | Avondale Ho | Clarkston Ltd | 0 | 0 | 4 | 4 |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed |  | Deliverable
876 | H29 | HLA | Private Dev. | Whitecross | Whitecross | Miller Homes | 0 | 0 | 225 | 225 |  | 0 | 40 | 40 | 40 | 40 | 40 | 25 | 0 | 0 | 0 | 0 | LDP/out |  | Deliverable
739 | H21 | HLA | Private Dev. | Hillcrest | Shieldhill | Persimmon Homes East Scotland | 36 | 32 | 23 | 55 |  | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP/detailed |  | Deliverable
666 |  | HLA | Landowner | Boagstown Farm | Avonbridge | Mr W Waugh | 3 | 0 | 1 | 1 |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed |  | Deliverable
631 | MU08 | HLA | Private Dev. | Steins Brickworks | Allandale | Allandale Properties Ltd | 0 | 0 | 140 | 140 |  | 0 | 0 | 40 | 40 | 40 | 20 | 0 | 0 | 0 | 0 | 0 | LDP/detailed extant |  | Deliverable with Constraints | Access issue to be resolved. Planning application to be approved. Housebuilder to be confirmed.
594 | H26 | HLA | Landowner | Avonbridge Road | Slamannan | Balquest Llp | 0 | 0 | 10 | 10 |  | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Deliverable | Planning application from housebuilder
380 | H23 | HLA | Housing Assoc. | Cockmalane | California | Link HA | 0 | 0 | 39 | 39 |  | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP/detailed |  | Deliverable
590 |  | HLA | Landowner | Manse Brae | Avonbridge | Mr W Jeffrey | 0 | 0 | 6 | 6 |  | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed |  | Deliverable with Constraints | Retrospective planning application to be approved
589 |  | HLA | Private Dev. | Linhouse Farm | Avonbridge | Mixed | 2 | 0 | 2 | 2 |  | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed |  | Deliverable
586 |  | HLA | Private Dev. | Myrehead Farm | Myrehead | Mixed | 2 | 3 | 5 | 8 |  | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed |  | Deliverable | Individual planning applications to be made.
658 | H28 | HLA | Private Dev. | Standburn West | Standburn | A Paterson/D Green | 1 | 0 | 29 | 29 |  | 1 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Deliverable with Constraints | Planning application to be made. Housebuilder to be confirmed.
358 | H27 | Non Contributing HLA | Landowner | Main Street | Slamannan | Mr Kelly | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Constrained | Flooding to be addressed. Planning application to be made. Marketability to be evidenced. Housebuilder to be confirmed.
708 | H22 | Non Contributing HLA | Landowner | Bridgend Road | Avonbridge | Mr C Miller | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Constrained | Planning application to be made. Housebuilder to be confirmed.
642 | H25 | Non Contributing HLA | Private Dev. | Slamannan Road | Limerigg | Manor Forrest | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Constrained | Planning application to be made. Housebuilder to be confirmed.
588 |  | Non Contributing HLA | Landowner | Carriden Steadings | Muirhouses | Mr & Mrs Tom Barkhouse | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed extant |  | Constrained | Planning consent to be implemented.
534 | H24 | Non Contributing HLA | Private Dev. | Church Road | California | Mixed | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Constrained | Planning application to be made. Housebuilder to be confirmed.
100 |  | Non Contributing HLA | Private Dev. | Church Road 1 | California | Mixed | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed extant |  | Constrained | Planning consent to be implemented. Housebuilder to be confirmed.
421 |  | Non Contributing HLA | Landowner | Station Road 1 | Whitecross | Unknown | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | detailed extant |  | Undeliverable | Planning consent to be implemented. Housebuilder to be confirmed.
340 | BUS02 | Non Contributing HLA | Landowner | Manuel Works | Whitecross | Arrochar Developments Ltd | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | outline |  | Constrained | Planning consent to be implemented. Housebuilder to be confirmed.
41 |  | HLA | Landowner | Slamannan Road North | Avonbridge | Mr G Melville | 0 | 0 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | outline |  | Deliverable with Constraints | Planning application to be approved followed by detailed application.
522 | H58 | Non Contributing HLA | Landowner | Slamannan Road 1 | Limerigg | Unknown | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LDP |  | Deliverable with Constraints | Planning application to be made. Housebuilder to be confirmed.
[7 empty] | 700 | 256 | 4712 | 4968 | 2226 | 344 | 459 | 750 | 873 | 643 | 701 | 355 | 261 | 126 | 90 | 366
4968
0