## HLA25_26
Housing Land Audit 2025/26 - all sites | [11 empty] | Short Term |  |  | Medium Term |  |  | Long Term | [16 empty] | Split indicative if not confirmed | [5 empty] | March 2026
Status | Site Ref | LDP2 | Developer Type | Site Name | Settlement | Company Name | Complete 31/3/25 | Under construction | Remainder | Total under construction and remainder | Non contributing/constrained | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035+ | Disputed | Permission Status | Deliverability Status | Action Required | Application Ref No | Date of consent | Expires | Grid Ref. Easting | Grid Ref. Northing | AREA (ha's) | Date in HLA record system | Main Tenure | Affordable | Private | Flats | Houses | Site Type Name | VDL Site | Primary School
Bo'ness
HLA | 555 | H06 | Housing Assoc. | Union Street | Bo'ness | Link HA | 0 | 30 | 0 | 30 |  | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP/detailed | Deliverable |  | 20/191/ful | 15/7/21 | 14/7/24 | 300058.81 | 681765.58 | 0.33 | 2006-02-07 | General Needs Rented | 30 |  | 30 |  | BROWNFIELD |  | BO'NESS
HLA | 665 |  | Landowner | Bridgeness Road 3 | Bo'ness | Mr M Sroka | 0 | 0 | 6 | 6 |  | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed | Deliverable |  | 10/321, 17/628, 24/0422 | 6/5/11, 21/2/18, 14/3/25 | 6/5/14, 20/2/2, 13/3/28 | 301648.52 | 681390.63 | 0.06 | 2009-12-17 | Mainstream (Flats) |  | 6 | 6 |  | GREENFIELD |  | GRANGE
HLA | 695 | MU02 | Private Dev. | Drum Farm South | Bo'ness | Miller Homes | 19 | 51 | 145 | 196 |  | 69 | 63 | 50 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP/detailed | Deliverable |  | 12/231, 22/105 | 13/5/13, 11/5/23 | extant, 10/5/26 | 301186.88 | 680564.19 | 13.28 | 2011-04-20 | Mainstream (Housing) | 29 | 167 | 4 | 192 | GREENFIELD |  | GRANGE
HLA | 813 | H55 | Private Dev. | Crawfield Road Phase 2 | Bo'ness | Cala | 0 | 0 | 226 | 226 |  | 0 | 10 | 36 | 36 | 36 | 36 | 36 | 36 | 0 | 0 | 0 |  | LDP/detailed | Deliverable |  | P/19/0409/PPP, 22/009 | refused, 16/4/24 | , 15/4/27 | 299203 | 679819 | 28.8 | 2017-05-15 | Mainstream (Housing) | 67 | 386 | 12 | 441 | GREENFIELD |  | DEANBURN
HLA | 813 | H56 | Private Dev. | Crawfield Road Phase 1 | Bo'ness | Robertson | 0 | 0 | 227 | 227 |  | 21 | 26 | 43 | 43 | 26 | 26 | 26 | 16 |  |  |  |  | LDP/detailed | Deliverable |  | P/19/0409/PPP, 22/009 | refused, 16/4/24 | , 15/4/27 | 299203 | 679819 |  | 2017-05-15 | Mainstream (Housing) |  |  |  |  | GREENFIELD |  | DEANBURN
HLA | 842 | H56 | Private Dev. | North Bank Farm | Bo'ness | Miller Homes/Persimmon | 102 | 8 | 68 | 76 |  | 17 | 36 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP/detailed | Deliverable |  | 19/129, 20/0519, 24/0535 | 20/10/20, 8/6/21, pending | 19/10/23, 7/6/23 | 300996 | 680324 | 13 | 2017-05-20 | Mainstream (Housing) |  | 76 |  | 76 | GREENFIELD |  | GRANGE
HLA | 903 |  | Landowner | Northbank Farm Holding | Bo'ness | Northbank Farm Holding | 0 | 0 | 11 | 11 |  | 0 | 0 | 1 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed | Deliverable |  | 21/0313, 25/0075 | 3/2/23, 18/9/25 | 2/2/26, 17/9/27 | 301093 | 680103 | 1.48 | 2024-04-01 | Mainstream (Housing) |  | 11 |  | 11 | BROWNFIELD |  | GRANGE
HLA | 390 | H01 | Private Dev. | Drum Farm North | Bo'ness | Ogilvie Homes | 105 | 0 | 90 | 90 |  | 0 | 0 | 0 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 0 |  | LDP/det | Deliverable with Constraints | Detailed planning consent required | 2004/63, 07/275, 08/915, 17/497, 18/432 | appeal upheld, appeal upheld, 5/5/09, 17/8/18, 5/8/20 | 5/5/14, 16/8/21, 4/8/23 | 301400.68 | 681043.22 | 11.22 | 2003-11-12 | Mainstream (Housing) |  | 90 |  | 90 | GREENFIELD |  | GRANGE
Non Contributing HLA | 63 | H05 | Landowner | Main Street A | Bo'ness | Unknown | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Deliverable with Constraints | No specific actions identified | 07/843, 18/0424 | refused,refused |  | 300065.67 | 681643.17 | 0.26 | 1999-04-01 | Mainstream (Flats) |  |  |  |  | BROWNFIELD |  | BO'NESS
Non Contributing HLA | 868 | MU03 | Landowner | Crawfield Lane | Bo'ness | Unknown | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Deliverable with Constraints | Identify landowner and developer intentions | 20/0539 | returned |  | 299652 | 680202 | 1.38 | 2019-10-03 | Affordable (Housing) |  |  |  |  | BROWNFIELD | F/BNES/046 | KINNEIL
Non Contributing HLA | 867 | MU01 | Landowner | Links Road | Bo'ness | Unknown | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Undeliverable | Not being promoted. Multiple ownerships, no specific actions identified. Site is unlikely to be able to address flood risk. |  |  |  | 300427 | 681588 | 1.1 | 2019-10-04 | Mainstream (Housing) |  |  |  |  | BROWNFIELD | F/BNES/054 | BO'NESS
Non Contributing HLA | 175 | H03 | Landowner | Kinglass Farm 2 | Bo'ness | Mr Robert Kirk | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Undeliverable | Access is not achievable without third party land | 10/482, 11/701, 12/414 | 7/3/11, withdrawn, 7/2/14 | 7/3/14, , 7/2/17 | 300914 | 680644.24 | 0.74 | 1999-04-01 | Mainstream (Housing) |  |  |  |  | GREENFIELD |  | GRANGE
Non Contributing HLA | 646 | H04 | Landowner | South Street | Bo'ness | H & K Estates Ltd | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Deliverable with Constraints | Housebuilder to be attached. Pipeline restrictions to be addressed. | 08/626, 14/0308 | 18/6/09, 18/9/15 | 18/6/14, 17/9/18 | 299997.87 | 681641.17 | 0.17 | 2008-10-01 | Mainstream (Flats) |  |  |  |  | BROWNFIELD |  | BO'NESS
Bonnybridge and Banknock
HLA | 437 | MU04 | Private Dev. | Banknock North | Banknock | Persimmon Homes North Scotland | 0 | 0 | 453 | 453 |  | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 103 |  | LDP/outline | Deliverable with Constraints | Planning consent to be issued | 10/360, 19/020, 19/79, 21/298, 23/178 | 28/9/16, 29/3/19, withdrawn, withdrawn, pending | 27/9/19, 28/3/21 | 278406.34 | 679530.28 | 26.3388 | 2004-02-17 | Mainstream (Housing) | 67 | 386 |  |  | BROWNFIELD | F/BONY/010 | BANKIER
HLA | 274 | H11 | Local Auth. | Seabegs Road | Bonnybridge | Falkirk Council | 0 | 0 | 31 | 31 |  | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | disputed | LDP | Deliverable with Constraints | Planning application from Council, SHIP funding to be confirmed |  |  |  | 282135.91 | 679777.88 | 1.1996 | 2000-08-18 | Affordable (Housing) | 31 |  |  | 31 | BROWNFIELD | F/BONY/067 | ANTONINE
Non Contributing HLA | 897 |  | Landowner | Glen Etive, Kilsyth Road | Haggs | Unknown | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | outline | Undeliverable |  | 21/0671, 24/0342 | 16/11/22, 29/11/24 | 15/11/25, 28/11/27 | 279556 | 679295 | 0.34 | 2023-07-24 | Mainstream (Housing) |  |  |  |  | UNKNOWN |  | BANKIER
HLA | 869 | H53 | Landowner | Cumbernauld Road | Longcroft | Mr D Gallacher | 0 | 0 | 4 | 4 |  | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP/detailed | Deliverable |  | 23/0334, 25/0550 | 17/10/23, pending | 16/10/26 | 279519 | 679183 | 0.5 | 2019-10-03 | Mainstream (Housing) |  | 4 |  | 4 | GREENFIELD |  | BANKIER
HLA | 578 | MU05 | Landowner | Bonnybridge Town Centre | Bonnybridge | Unknown | 0 | 0 | 5 | 5 |  | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP/detailed | Deliverable with Constraints | New planning application to be to be approved | 06/631, 21/076, 22/519, P/26/0057/FUL | 8/12/06, withdrawn, 29/3/23, pending | 8/12/11, 28/3/26 | 282433.72 | 680230.57 | 0.88 | 2007-01-03 | Mainstream (Housing) |  | 5 |  | 5 | BROWNFIELD |  | BONNYBRIDGE
HLA | 436 | H08 | Local Auth. | Banknock South | Banknock | Falkirk Council | 0 | 0 | 106 | 106 |  | 0 | 0 | 0 | 0 | 0 | 26 | 37 | 43 | 0 | 0 | 0 | disputed | LDP/detailed | Deliverable with Constraints | SHIP funding to be confirmed. | 20/044/ful | 4/4/22 | 3/4/25 | 277693.19 | 678998.29 | 5.6438 | 2004-10-17 | Mainstream (Housing) | 106 |  | 24 | 82 | GREENFIELD |  | BANKIER
HLA | 327 | H12 | Landowner | Garngrew Road | Banknock | Hamilton Brown Developments | 0 | 0 | 19 | 19 |  | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 |  | LDP | Deliverable with Constraints | S75 to be signed | 10/633 FUL, 22/35 | 3/3/11, minded to grant | 2/3/14 | 278931.1 | 678989.39 | 4.1 | 12/9/202 | Mainstream (Housing) |  | 19 |  | 19 | GREENFIELD |  | BANKIER
HLA | 80/176 | H08 | Private Dev. | Bankock South (Bankier Distillery/Wellpark Road) | Banknock | Muir Homes Ltd | 0 | 0 | 78 | 78 |  | 0 | 0 | 0 | 35 | 35 | 8 | 0 | 0 | 0 | 0 | 0 |  | LDP | Deliverable | planning consent to be issued | 24/0141 | mined to grant |  | 277801.91 | 678893.45 | 3.91 | 1999-04-01 | Mainstream (Housing) | 11 | 67 | 4 | 74 | BROWNFIELD |  | BANKIER
HLA | 348 | H09 | Private Dev. | Dennyloanhead | Dennyloanhead | Persimmon Homes East Scotland | 0 | 0 | 562 | 562 |  | 0 | 55 | 61 | 50 | 40 | 40 | 50 | 62 | 51 | 40 | 113 |  | LDP/detailed | Deliverable |  | 09/508, 19/647, 20/188, 21/235, P/22/0245/MSC, 22/0246 | 4/10/17, 20/1/21, 20/1/21, 4/6/21, 28/6/24, 27/3/25 | 3/10/20, 19/1/23, 19/1/23, 3/6/23, 27/6/26, 26/3/28 | 280306.98 | 679949.26 | 32.2 | 2002-09-20 | Mixed | 87 | 475 | 24 | 538 | GREENFIELD | F/DENY/044 | HEAD OF MUIR
Non Contributing HLA | 862 |  | Landowner | 30-32 High Street | Bonnybridge | Unknown | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed | Constrained | Conversion works to be completed | 18/0332 | 5/4/19 | 4/4/22 | 282219 | 680400 | 0.03 | 2019-10-01 | Mainstream (Flats) |  |  |  |  | BROWNFIELD |  | BONNYBRIDGE
HLA | 491 | MU20 | Private Dev. | East Bonnybridge | Bonnybridge | Lochay Homes Ltd | 0 | 0 | 30 | 30 |  | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | disputed | LDP | Deliverable with Constraints | Planning application to be approved | 09/0431, 26/0083/FUL | refused, pending |  | 283565.64 | 680668.39 | 7.3525 | 2004-12-08 | Mainstream (Housing) |  | 30 |  | 30 | GREENFIELD |  | BONNYBRIDGE
Non Contributing HLA | 565 |  | Private Dev. | Bridge Street | Bonnybridge | Antonine Property Developments Group Ltd | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed | Deliverable with Constraints | planning consent to be implemented or revised application to be made | 07/0635, 14/0069, 14/0233, P/07/0635/FUL | 17/10/18, 6/6/14, 17/10/18 | 16/10/21 6/6/17, 16/10/21 | 282306.74 | 680075.71 | 1.17 | 2006-02-14 | Mainstream (Flats) |  |  |  |  | MIXED |  | BONNYBRIDGE
Non Contributing HLA | 597 | H10 | Private Dev. | Broomhill Road | High Bonnybridge | Manor Forrest | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Deliverable with Constraints | Planning application to be submitted | 07/0069, 11/0039, 11/142, 15/631, 19/533 | 8/2/08, 30/11/12, pending, 14/9/16, 23/4/21 | 8/2/13, 30/11/15, refused, 13/9/19, 22/4/24 | 282759.58 | 679581.02 | 0.76 | 2007-02-08 | Mainstream (Housing) |  |  |  |  | BROWNFIELD |  | ANTONINE
Non Contributing HLA | 638 |  | Landowner | Garngrew Road North | Haggs | Mr A Brown | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | outline | Undeliverable |  | 09/352, 10/288, 10/362, 11,771, 11/591, 10/230, 10/229, 10/632, 18/0743 | 24/11/09, withdrawn, 08/02/11, 24/2/12, withdrawn, 5/7/10, 16/9/10, 8/2/11, 31/7/19 | 24/11/12, 08/02/14, 24/2/15, , 5/7/13, 16/9/13, 8/2/14, 30/7/22 | 278906.64 | 679132.39 | 0.46 | 2008-05-28 | Mainstream (Housing) |  |  |  |  | GREENFIELD |  | BANKIER
Braes Urban Area
HLA | 847 | H18 | Private Dev. | Parkhall Farm 5 | Maddiston | Ecosse Regeneration | 0 | 0 | 70 | 70 |  | 0 | 0 | 0 | 10 | 20 | 20 | 20 | 0 | 0 | 0 | 0 |  | outline | Deliverable with Constraints | Planning application to be submitted. Housebuilder to be confirmed. | 16/0756, 25/0450 | 9/12/22, pending | 8/12/25 | 294689 | 677429 | 8.54 | 2018-05-03 | Mainstream (Housing) |  | 70 |  | 70 | GREENFIELD |  | MADDISTON
HLA | 898 |  | Landowner | Greenpark Drive | Polmont | Unknown | 5 | 1 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed | Deliverable |  | 20/0617 | 30/9/22 | 29/9/25 | 293659 | 678994 | 0.405 | 2023-07-25 | Mainstream (Housing) |  | 1 |  | 1 | GREENFIELD |  | ST MARGARET'S
HLA | 874 | H20 | Private Dev. | Redding Park 2 | Reddingmuirhead | Gracey Ltd | 0 | 2 | 38 | 40 |  | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP/det | Deliverable |  | 20/429 | 29/4/21 | 28/4/24 | 291121 | 678057 | 1.2 | 2019-10-24 | Affordable (Housing) |  | 40 |  | 40 | BROWNFIELD |  | WESTQUARTER
HLA | 531 | H57 | Private Dev. | Maddiston Fire Station | Maddiston | Miller M2 Developments | 95 | 1 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP/outline | Deliverable |  | 17/0347, P/21/0301/MSC | 23/9/19, 10/12/21 | 22/9/22, 09/12/23 | 293820.9 | 676676.92 | 2.2868 | 2005-01-19 | Mainstream (Housing) |  | 1 |  | 1 | BROWNFIELD |  | MADDISTON
HLA | 246 | MU06 | Private Dev. | Gilston | Polmont | Cala | 0 | 0 | 345 | 345 |  | 3 | 48 | 72 | 74 | 73 | 75 | 0 | 0 | 0 | 0 | 0 |  | LDP/detailed | Deliverable |  | 07/803, 13/315, 17/0332, 20/0493 | extant, 6/9/13, refused, 29/4/24 | 5/9/15 28/4/27 | 294708.12 | 678104.83 | 67.16 | 2000-08-17 | Mainstream (Housing) | 125 | 375 | 30 | 470 | GREENFIELD |  | ST MARGARET'S
HLA | 246 | MU06 | Private Dev. | Gilston 2 | Polmont | Taylor Wimpey | 0 | 0 | 155 | 155 |  | Short Term 2025/26: 0; Short Term 2026/27: 30; Short Term 2027/28: 35; Medium Term 2028/29: 35; Medium Term 2029/30: 35; Medium Term 2030/31: 20 | [7 empty] | 294708.12 | 678104.83 | 67.16 | 2000-08-17 | Mainstream (Housing) |  |  |  |  | GREENFIELD |  | ST MARGARET'S
HLA | 619 |  | Housing Assoc. | Westquarter Avenue | Westquarter | Link Group | 0 | 0 | 17 | 17 |  | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed | Deliverable |  | 07/452, 14/428, 22/0494 | withdrawn, 7/1/16, 14/7/23 | 6/1/19, 13/7/26 | 291265.6 | 678795.33 | 0.25 | 2008-01-15 | General Needs Rented | 17 |  | 8 | 9 | BROWNFIELD |  | WESTQUARTER
Non Contributing HLA | 234 | H17 | Landowner | Toravon Farm | Maddiston | Unknown | 0 | 0 | 0 | 0 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Deliverable with Constraints | Planning application to be submitted. Housebuilder to be confirmed. |  |  |  | 294472.47 | 676649.37 | 6.2428 | 2000-08-15 | Mainstream (Housing) |  |  |  |  | GREENFIELD |  | MADDISTON
Non Contributing HLA | 724 | H54 | Landowner | The Haining | Maddiston | Ion Care And Support Services | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Deliverable with Constraints | MSC planning application to be submitted. Housebuilder to be confirmed. | 14/483, 19/0428/PPP | refused, 13/7/23 | 12/7/26 | 294659.36 | 677243.72 | 3.57 | 2012-08-09 | Mainstream (Housing) |  |  |  |  | GREENFIELD |  | MADDISTON
Non Contributing HLA | 746 | H13 | Private Dev. | Parkhall Farm 1 | Maddiston | Manor Forrest | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Deliverable with Constraints | Planning application to be submitted. Housebuilder to be confirmed. | 14/707 | withdrawn |  | 294433.06 | 677053.57 | 4.23 | 2015-01-26 | Mainstream (Housing) |  |  |  |  | GREENFIELD |  | MADDISTON
Non Contributing HLA | 877 | H15 | Private Dev. | Parkhall Farm 3 | Maddiston | Lochay Homes Ltd | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Deliverable with Constraints | Multiple ownerships and flood risk to be addressed. |  |  |  | 294626 | 677045 | 4.6 | 2020-06-01 | Mainstream (Housing) |  |  |  |  | GREENFIELD | F/POLM/061, F/POLM/062 | MADDISTON
Denny
HLA | 697 | H32 | Private Dev. | Mydub 2 | Denny | Avant Homes | 0 | 0 | 244 | 244 |  | 0 | 20 | 50 | 84 | 50 | 40 | 0 | 0 | 0 | 0 | 0 |  | LDP | Deliverable | Planning application to be approved | 21/112, 21/111, 21/566, 21/569 | pending, withdrawn, pending, pending |  | 281767.43 | 681946.36 | 12.73 | 2011-04-21 | Mainstream (Housing) | 36 | 208 |  |  | GREENFIELD |  | DENNY
HLA | 825 | H59 | Private Dev. | Rosebank North | Dunipace | Ogilvie Homes | 0 | 0 | 130 | 130 |  | 28 | 34 | 25 | 25 | 18 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP/detailed | Deliverable | Phase 3 application to be submitted. | 21/0723, 25/0519 | 31/10/2024, pending | 2027-10-30 | 280689 | 684319 | 6.4 | 2017-05-23 | Mainstream (Housing) | 19 | 111 |  |  | GREENFIELD |  | DUNIPACE
HLA | 669 |  | Landowner | Annet Road | Head Of Muir | Mr N Khan | 3 | 1 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed | Deliverable |  | 09/872, 11/457, 17/0774, 21/496/FUL | 2/12/10, 19/9/11, 28/9/18, 11/3/22 | 2/12/13, 19/9/14, 27/9/21, 10/3/25 | 280669.89 | 680565.9 | 0.26 | 2009-12-17 | Mainstream (Housing) |  | 1 |  | 1 | GREENFIELD |  | HEAD OF MUIR
HLA | 579 | H33 | Private Dev. | Carrongrove Mill | Stoneywood | Mactaggart/Mickel | 83 | 0 | 123 | 123 |  | 0 | 0 | 25 | 25 | 25 | 25 | 23 | 0 | 0 | 0 | 0 |  | LDP/det | Deliverable | S75 to be amended | 08/296, 16/426, 16/429, 24/0313 | 24/5/12, 24/2/17, 1/3/17, pending | 24/5/15, 23/2/20, 29/2/20 | 279609.67 | 682999.14 | 5.07 | 2007-01-04 | Mainstream (Housing) |  | 123 |  | 123 | BROWNFIELD | F/DENY/040 | DENNY
HLA | 503 | MU09 | Private Dev. | Broad Street | Denny | Cruden Homes (East) | 0 | 0 | 224 | 224 |  | 0 | 0 | 37 | 46 | 67 | 36 | 29 | 9 | 0 | 0 | 0 |  | LDP | Deliverable | Planning application to be approved | 25/0405 | pending |  | 281930.65 | 682738.43 | 16.65 | 2004-12-08 | Mainstream (Housing) | 33 | 191 |  |  | GREENFIELD |  | DENNY
HLA | 426 | H30 | Local Auth. | Former Denny High School (Phase 1) | Denny | Falkirk Council | 0 | 0 | 137 | 137 |  | 0 | 0 | 37 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP/detailed | Deliverable |  | 04/1027, 19/795 | 6/4/05, 26/6/20 | 6/4/08, 25/6/23 | 281042.72 | 681742.53 | 12.95 | 2004-02-10 | Affordable (Housing) | 137 |  | 32 | 105 | BROWNFIELD | F/DENY/038 | NETHERMAINS
HLA |  | H30 | Private Dev. | Former Denny High School (Phase 2) | Denny | Unknown | 0 | 0 | 63 | 63 |  | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | disputed | LDP | Deliverable with Constraints | Site to be marketed. Housebuilder to be attached. Planning consent required. |  | 6/4/05, 26/6/20 | 6/4/08, 25/6/23 | 281042.72 | 681742.53 |  | 2004-02-10 | Mainstream (Housing) |  | 63 |  | 63 | BROWNFIELD | F/DENY/038
Non Contributing HLA | 870 | MU10 | Local Auth. | Church Walk | Denny | Falkirk Council | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Constrained | No actions identified |  |  |  | 281111 | 682880 | 0.7 | 2019-10-03 | Mainstream (Housing) |  |  |  |  | BROWNFIELD | F/DENY/041 | DENNY
Falkirk
Non Contributing HLA | 799 |  | Landowner | 1 Carradale Avenue | Tamfourhill | Unknown | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed | Deliverable with Constraints | Housebuilder to be attached. Planning application to be made. | 18/0463 | 25/4/19 | 24/4/22 | 286596 | 679618 | 0.2 | 2019-06-30 | Affordable (Housing) |  |  |  |  | BROWNFIELD | F/FALK/125 | BANTASKIN
Non Contributing HLA | 250 | MU11 | Local Auth. | Portdownie | Camelon | Falkirk Council | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Constrained | Site remediation. Development partner required. | 10/512 | withdrawn |  | 286354.16 | 679985.46 | 13.62 | 2000-08-17 | Mixed |  |  |  |  | BROWNFIELD | F/FALK/044 | BANTASKIN
HLA | 316 |  | Private Dev. | Glenochil Road | Falkirk | Mixed | 2 | 1 | 1 | 2 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed | Deliverable | Application to be made for final plot | 01/0867, 05/991, 07/276, 08/572, 14/478, 20/151 | 14/11/02, 12/9/06, 26/4/07, 11/12/08, withdrawn, 1/12/20 | 14/11/07, 12/9/11, 26/4/12, 11/12/13, 31/11/23 | 288092.17 | 679214.38 | 0.21 | 2002-08-30 | Mainstream (Housing) |  | 2 |  | 2 | GREENFIELD |  | COMELY PARK
HLA | 383 | H43 | Landowner | Westburn Avenue | Falkirk | Forth Valley Health Board | 0 | 0 | 100 | 100 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 |  | LDP | Deliverable with Constraints | Site masterplan required. Site to be marketed. |  |  |  | 288123.33 | 679723.29 | 11.9977 | 2002-11-28 | Mainstream (Housing) | 15 | 85 |  |  | BROWNFIELD |  | COMELY PARK
HLA | 509 |  | Private Dev. | Seaforth Road | Bainsford | Roubaix Developments Ltd | 0 | 0 | 9 | 9 |  | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | none | Deliverable | Planning consent to be implemented | 05/1166, 11/87, 23/0442 | 21/2/06, 20/5/11, 10/7/24 | 21/2/11, 20/5/14, 9/7/27 | 289169.44 | 682134.25 | 0.12 | 2004-12-06 | Mainstream (Housing) |  | 9 |  | 9 | BROWNFIELD |  | LANGLEES
HLA | 585 | MU16 | Landowner | Falkirk Gateway | Falkirk | Hargreaves Land Ltd | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 |  | LDP | Deliverable with Constraints | Developable area to be confirmed by FRA. Alignment with wider masterplan for site to be confirmed. Housebuild required to be attached to site. |  |  |  | 290444.82 | 680936.68 | 59.34 | 2007-01-10 | Mainstream (Housing) | 7 | 43 |  |  | GREENFIELD |  | VICTORIA
HLA | 610 |  | Private Dev. | Maggie Woods Loan | Falkirk | Casa Homes (Scotland) Ltd | 8 | 4 | 0 | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed | Deliverable |  | 07/0680, 10/435, P/21/0310/FUL, P/22/0063/FUL | 20/12/07, 7/1/11, withdrawn, 6/9/22 | 20/12/12, 7/1/14 5/9/25 | 287848.42 | 679685.5 | 0.35 | 2010-01-14 | Mainstream (Flats) |  | 4 | 4 |  | BROWNFIELD |  | COMELY PARK
HLA | 704 | H42 | Local Auth. | Woodend Farm | Hallglen | Falkirk Council | 32 | 79 | 0 | 79 |  | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP/detailed | Deliverable |  | P/19/0453/FUL | 26/6/20 | 25/6/23 | 290028.52 | 678614.85 | 4.56 | 2011-04-27 | Mainstream (Housing) | 79 |  | 10 | 69 | GREENFIELD |  | HALLGLEN
HLA | 705 | H39 | Landowner | Cauldhame Farm | Falkirk | Mr G Steel/Elma Steel | 0 | 0 | 200 | 200 |  | 0 | 0 | 0 | 0 | 20 | 55 | 55 | 45 | 25 | 0 | 0 |  | LDP | Deliverable with Constraints | Housebuilder to be confirmed. Planning aplication to be submitted. |  |  |  | 287880.12 | 681157.91 | 14.19 | 2011-04-27 | Mainstream (Housing) | 30 | 170 |  |  | GREENFIELD |  | LANGLEES
HLA | 801 | MU17 | Housing Assoc. | Carron Road | Falkirk | Wheatley Group | 0 | 0 | 82 | 82 |  | 0 | 0 | 44 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Deliverable | S75 to be signed | 25/0085 | minded to grant |  | 288367 | 681748 | 2 | 2020-08-31 | Affordable (Housing) | 82 |  | 56 | 26 | BROWNFIELD |  | LANGLEES
HLA | 863 |  | Landowner | Bean Row | Falkirk | Vkrr Investments Ltd | 4 | 0 | 1 | 1 |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed | Deliverable |  | 19/237, 20/81 | 13/6/19, 20/7/20 | 12/6/22, 19/7/23 | 288862 | 679840 | 0.1 | 2019-01-01 | Mainstream (Flats) |  | 1 |  | 1 | BROWNFIELD |  | COMELY PARK
HLA | 889 |  | Private Dev. | 150 High Street | Falkirk | Hannigan Hotels Ltd | 0 | 0 | 7 | 7 |  | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed | Deliverable with Constraints | Planning consent to be implemented | 20/566, 23/0624, 24/0253, 25/0376 | 27/4/21, withdrawn, 10/9/24, pending | 26/4/24, 9/9/27 | 288921 | 679897 | 0.15 | 2021-08-30 | Mainstream (Flats) |  | 7 | 7 |  | BROWNFIELD |  | COMELY PARK
HLA | 908 |  | Private Dev. | Alma Street East | Falkirk | DNG Property Services Ltd | 0 | 0 | 4 | 4 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed | Deliverable | Planning consent to be implemented | 23/0471 | 6/11/24 | 5/11/27 | 288680 | 680663 | 0.09 | 2025-10-14 | Mainstream (Housing) |  | 4 |  | 4 | BROWNFIELD |  | COMELY PARK
HLA | 901 |  | Private Dev. | Bankside | Bankside | McMillan Property Developments Ltd | 1 | 4 | 0 | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed | Deliverable |  | 22/0186 | 4/11/22 | 3/11/25 | 289211 | 681353 | 0.11 | 2023-07-25 | Mainstream (Housing) |  | 4 |  | 4 | BROWNFIELD |  | BAINSFORD
Non Contributing HLA | 904 |  | Landowner | Canal Street | Falkirk | Unknown | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed | Deliverable with Constraints | Planning consent to be implemented | 23/520 | 20/12/23 | 21/12/26 | 288766 | 681113 | 0.02 | 2024-04-01 | Mainstream (Flats) |  |  |  |  | BROWNFIELD |  | COMELY PARK
Non Contributing HLA | 722 | H41 | Private Dev. | Grangemouth Road | Falkirk | Gannet Developments Ltd | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Undeliverable | No actions identified |  |  |  | 289876.74 | 680622.32 | 7.23 | 2012-08-08 | Mainstream (Housing) |  |  |  |  | BROWNFIELD | F/FALK/127 | VICTORIA
Non Contributing HLA | 501 | H44 | Landowner | Firs Park | Falkirk | Mr A Mackin | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Constrained | Access to be resolved, potential for third party land to be required. | 13/0234 | 22/7/16 | 21/7/19 | 289183.47 | 680553.05 | 1.2557 | 2004-12-08 | Affordable (Housing) |  |  |  |  | BROWNFIELD | F/FALK/105 | VICTORIA
Non Contributing HLA | 872 | MU12 | Landowner | Grahamston | Falkirk | Unknown | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Constrained | no actions identified |  |  |  | 288722 | 680264 | 2.6 | 2019-10-14 | Mainstream (Flats) |  |  |  |  | BROWNFIELD |  | COMELY PARK
Non Contributing HLA | 888 |  | Private Dev. | Erskine Church, Hodge Street | Falkirk | Erskine Community Halls Ltd | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed extant | Deliverable with Constraints | Viability to be confirmed | 20/364 | 26/1/21 | 25/1/24 | 288521 | 679780 | 0.19 | 2021-08-30 | Mainstream (Flats) |  |  |  |  | BROWNFIELD |  | COMELY PARK
Non Contributing HLA | 612 | MU14 | Private Dev. | Bank Street | Falkirk | J R Johnston Development Ltd | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Constrained | Site to be marketed, housebuilder to be confirmed | 07/771, 14/409 | 9/1/08, 11/11/15 | 9/1/13, 10/11/18 | 288873.62 | 680035.96 | 0.13 | 2007-01-14 | Mainstream (Flats) |  |  |  |  | BROWNFIELD |  | COMELY PARK
Non Contributing HLA | 562 | H36 | Landowner | Gowan Lane | Grahamston | Mr M Thompson (Nu-Car Auto Salvage Ltd) | 0 | 0 | 0 | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Constrained | Site to be marketed. Access to be resolved, potenial for wider development linked to adjacent sites | 07/518 | 30/3/16 | 29/3/19 | 288650.22 | 680913.24 | 2.18 | 2006-02-14 | Mainstream (Housing) |  |  |  |  | BROWNFIELD | F/FALK/111 | BAINSFORD
Non Contributing HLA | 899 |  | Landowner | Thornhill Road | Falkirk | Unknown | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed | Undeliverable | No actions identified | 21/0574, 24/0558 | 9/5/23, minded to grant | 8/5/26 | 289361 | 680602 | 0.31 | 2021-08-30 | Mainstream (Housing) |  |  |  |  | BROWNFIELD |  | VICTORIA
Non Contributing HLA | 563 | MU13 | Landowner | Callendar Riggs | Falkirk | Unknown | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Constrained | No actions identified |  |  |  | 289167.79 | 679869.72 | 1.98 | 2006-02-14 | Mainstream (Flats) |  |  |  |  | BROWNFIELD |  | COMELY PARK
Grangemouth
Non Contributing HLA | 871 | MU18 | Local Auth. | Grangemouth Town Centre | Grangemouth | Falkirk Council | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Constrained | Flood risk and major hazards to be addressed. |  |  |  | 292680 | 681995 | 6.5 | 2018-10-14 | Mainstream (Housing) |  |  |  |  | BROWNFIELD |  | BEANCROSS
HLA | 909 |  | Landowner | West of Thistle Avenue | Grangemouth | Unknown | 0 | 0 | 5 | 5 |  | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | outline | Deliverable with Constraints | Site being marketed, housebuilder to be confirmed. Planning application to be submitted | 24/0051 | 2024-06-21 | 2027-06-20 | 291809 | 680467 | 0.63 | 2018-10-14 |  |  | 5 |  | 5 | GREENFIELD |  | BEANCROSS
Non Contributing HLA | 875 | MU21 | Local Auth. | Glensburgh | Grangemouth | Falkirk Council | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Undeliverable | No actions identified |  |  |  | 291134 | 681791 | 4.46 | 2024-06-21 | Mainstream (Housing) |  |  |  |  | GREENFIELD |  | BEANCROSS
Larbert and Stenhousemuir
HLA | 885 | MU19 | Private Dev. | Hill Of Kinnaird 2 | Larbert | Cala/Persimmon | 0 | 0 | 70 | 70 |  | 0 | 0 | 30 | 30 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Deliverable | Planning application to be submitted |  |  |  | 287312 | 684276 | 8.7 | 2020-07-01 | Mainstream (Housing) | 17 | 53 |  |  | BROWNFIELD |  | Kinnaird
HLA | 902 |  | Private Dev. | Bothkennar Road | Carronshore | Tollbooth Property Ltd | 11 | 4 | 0 | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed | Deliverable |  | 22/0376 | 4/7/23 | 3/7/26 | 289517 | 683294 | 0.36 | 2023-07-25 | Mainstream (Housing) |  | 4 |  | 4 | BROWNFIELD |  | CARRONSHORE
HLA | 906 |  | Private Dev. | Stirling Road West | Larbert | Heritage Homes Ltd | 0 | 0 | 6 | 6 |  | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed | Deliverable | Planning consent to be implemented | 23/0327 | 13/8/24 | 12/8/27 | 284885 | 683512 | 1.3 | 2025-10-14 | Mainstream (Housing) |  | 6 |  | 6 | GREENFIELD |  | LARBERT VILLAGE
HLA | 833 | H60 | Private Dev. | Stirling Road | Larbert | Avant Homes | 94 | 2 | 0 | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP/detailed | Deliverable |  | 17/0632, 19/803 | 25/4/19, 15/12/20 | 24/4/22, 14/12/23 | 285468 | 682668 | 4.4 | 2017-05-24 | Mainstream (Housing) |  | 2 |  | 2 | GREENFIELD |  | LARBERT VILLAGE
Rural North
HLA | 315 |  | Landowner | Denovan Mains Farm | Denny | Mr D Graham | 3 | 0 | 4 | 4 |  | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed | Deliverable with Constraints | Site to be sold. Planning consent to be implemented. | 2001/0578, | 20/02/2002, | 20/02/2007, | 281691.49 | 683363.6 | 0.84 | 2002-08-30 | Mixed |  | 4 |  | 4 | GREENFIELD |  | DUNIPACE
HLA | 334 | H52 | Private Dev. | Mclaren Park | Torwood | Heritage Homes Ltd | 8 | 3 | 0 | 3 |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP/det | Deliverable |  | 09/781, 14/443, 20/330, 20/347 | 14/3/11,withdrawn, 10/2/21, 10/2/21 | 14/3/16, 9/2/24, 9/2/24 | 283880.92 | 685169.9 | 2.32 | 2002-09-12 | Mainstream (Housing) |  | 3 |  | 3 | GREENFIELD |  | LARBERT VILLAGE
HLA | 355 | H48 | Private Dev. | Castle View | Airth | Lochay Homes Ltd | 68 | 27 | 0 | 27 |  | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP/detailed | Deliverable |  | PRE/14/0001/PAN, 15/684, 16/644, 22/389 | withdrawn, 2/10/19, 6/7/23 | 1/10/22, 5/7/26 | 289682.24 | 687542.49 | 13.35 | 2002-09-26 | Unknown |  | 27 |  | 27 | GREENFIELD |  | AIRTH
HLA | 798 |  | Landowner | Braeface Road 1 | Banknock | Unknown | 5 | 1 | 3 | 4 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed | Deliverable | Plots to be sold and plot planning application submitted. | 12/0124, P/16/0660/MSC, 18/016, 18/048, 18/063, 18/0672, 19/649, 25/493, 25/448 | 3/4/14, 21/4/16, 21/2/18, 21/3/18, 21/3/18, 2/5/19, 27/4/23, pending, pending | 2/4/17, 20/4/19, 20/2/21, 20/3/21, 20/3/21, 1/5/22, 26/7/26 | 278027 | 679530 | 0.6 | 2015-07-01 | Mainstream (Housing) |  | 4 |  | 4 | GREENFIELD |  | BANKIER
HLA | 850 |  | Private Dev. | Burnhouse Farm | Dunipace | Rustic Eco Properties | 5 | 1 | 4 | 5 |  | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed | Deliverable | Plots to be sold and plot planning application submitted. | 17/0437 | 7/3/19 | 6/3/22 | 279583 | 684441 | 1.27 | 2018-05-09 | Mainstream (Housing) |  | 5 |  | 5 | BROWNFIELD |  | DUNIPACE
HLA | 886 |  | Private Dev. | Moss Road | Dunmore | Mixed | 0 | 0 | 10 | 10 |  | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 |  | outline/detailed | Deliverable | Plots to be sold and plot planning application submitted. | 19/722, 21/305 | 26/6/20, 27/6/22 | 25/6/23, 26/7/25 | 287096 | 689561 | 1.04 | 2021-08-30 | Mainstream (Housing) |  | 10 |  | 10 | GREENFIELD |  | AIRTH
HLA | 890 |  | Private Dev. | South Bellsdyke Farm | Brackenlees | Rewd Group | 0 | 0 | 7 | 7 |  | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 |  | detailed | Deliverable |  | 20/0026, 24/0400, 25/320 | 11/6/21, 1/11/24, 1/12/25 | 10/6/24, 31/10/27,30/11/28 | 290574 | 684797 | 0.8 | 2021-08-30 | Mainstream (Housing) |  | 7 |  | 7 | BROWNFIELD |  | AIRTH
Non Contributing HLA | 326 | H49 | Private Dev. | Airth Castle South | Airth | Stewart Homes (Scotland) Ltd | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Deliverable with Constraints | Site to be marketed, housebuilder to be confirmed. Planning application to be submitted. | 04/178 | 14/10/15 | 13/10/18 | 290158.41 | 686899.69 | 2.22 | 2002-09-12 | Mainstream (Housing) |  |  |  |  | GREENFIELD |  | AIRTH
Non Contributing HLA | 258 |  | Landowner | Dunmore House | Dunmore | Mrs Sutherland | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | outline extant | Undeliverable |  | 2002/0542, 06/378, 06/1099 | 02/05/2003, withdrawn, 31/3/16 | 02/05/2006, 30/3/19 | 288665.66 | 689071.09 | 68.33 | 2000-08-17 | Mainstream (Housing) |  |  |  |  | GREENFIELD | F/RUR/016 | AIRTH
HLA | 333 | H50 | Landowner | The Glebe | Airth | Church Of Scotland General Trustees | 0 | 0 | 40 | 40 |  | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 |  | LDP | Deliverable with Constraints | Site to be marketed, housebuilder to be confirmed, planning application submitted. |  |  |  | 289585.79 | 687981.36 | 0.95 | 2002-09-12 | Unknown | 10 | 30 |  |  | GREENFIELD |  | AIRTH
Non Contributing HLA | 685 | H48 | Private Dev. | Castle View 1 | Airth | Mr P Mulholland | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP/detailed extant | Deliverable with Constraints | Housebuilder to be confirmed. Planning application submitted if original consent not developed. | 09/526, 23/0450 | 25/11/10, 24/11/23 | 25/11/13, 23/11/26 | 289832.93 | 687233.96 | 1.96 | 2010-09-16 | Mainstream (Housing) |  |  |  |  | GREENFIELD |  | AIRTH
Rural South
HLA | 884 |  | Private Dev. | Hillcrest Plots | Shieldhill | Mixed | 3 | 1 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | outline/detailed | Deliverable |  | 16/215, 18/0015, 18/726, 20/628, 20/490, 22/279, 22/641 | 10/7/17, 13/9/18, 15/11/22, 30/11/22, 19/3/21, 15/2/23, 18/7/23 | 9/7/20, 12/9/21, 14/11/25, 29/11/25, 18/3/24, 14/2/26, 17/7/26 | 290665 | 677375 | 0.519 | 2018-05-09 | Mainstream (Housing) |  | 1 |  | 1 | GREENFIELD |  | SHIELDHILL
HLA | 900 |  | Private Dev. | Avondale House | Avondale Ho | Clarkston Ltd | 0 | 0 | 4 | 4 |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed | Deliverable |  | 21/0572 | 1/7/22 | 30/6/25 | 295473 | 679239 | 0.64 | 2023-07-25 | Mainstream (Housing) |  | 4 |  | 4 | BROWNFIELD |  | ST MARGARET'S
HLA | 876 | H29 | Private Dev. | Whitecross | Whitecross | Miller Homes | 0 | 0 | 225 | 225 |  | 0 | 40 | 40 | 40 | 40 | 40 | 25 | 0 | 0 | 0 | 0 |  | LDP/out | Deliverable |  | P/17/0797/PPP, P/22/0042/MSC | 25/3/21, 12/5/25 | 24/3/24, 11/5/27 | 296534 | 676580 | 13.1 | 2020-06-01 | Mainstream (Housing) | 24 | 201 | 24 | 201 | GREENFIELD |  | WHITECROSS
HLA | 739 | H21 | Private Dev. | Hillcrest | Shieldhill | Persimmon Homes East Scotland | 36 | 32 | 23 | 55 |  | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP/detailed | Deliverable |  | 16/706, 17/504 | refused, 28/10/22 | 27/10/25 | 290577.07 | 677413.17 | 5.77 | 2013-04-25 | Mainstream (Housing) |  | 55 |  | 55 | GREENFIELD |  | SHIELDHILL
HLA | 666 |  | Landowner | Boagstown Farm | Avonbridge | Mr W Waugh | 3 | 0 | 1 | 1 |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed | Deliverable |  | 09/0018, 12/417, 15/472, 19/042 | 20/8/09, 20/11/12, 9/12/15, 26/4/19 | 20/8/12, 20/11/15, 8/12/18, 25/4/22 | 289314.83 | 673849.2 | 0.78 | 2009-12-17 | Mainstream (Housing) |  | 1 |  | 1 | BROWNFIELD |  | SLAMANNAN
HLA | 631 | MU08 | Private Dev. | Steins Brickworks | Allandale | Allandale Properties Ltd | 0 | 0 | 140 | 140 |  | 0 | 0 | 40 | 40 | 40 | 20 | 0 | 0 | 0 | 0 | 0 |  | LDP/detailed extant | Deliverable with Constraints | Access issue to be resolved. Planning application to be approved. Housebuilder to be confirmed. | 11/759, 22/0021 | 20/11/14, pending | 19/11/17 | 279753.82 | 678452.82 | 10.53 | 2008-02-20 | Mainstream (Housing) | 21 | 119 |  | 140 | BROWNFIELD | F/RUR/028 | ANTONINE
HLA | 594 | H26 | Landowner | Avonbridge Road | Slamannan | Balquest Llp | 0 | 0 | 10 | 10 |  | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Deliverable | Planning application from housebuilder |  |  |  | 285837 | 672994.62 | 1.81 | 2007-01-15 | Mainstream (Housing) |  | 10 |  | 10 | BROWNFIELD |  | SLAMANNAN
HLA | 380 | H23 | Housing Assoc. | Cockmalane | California | Link HA | 0 | 0 | 39 | 39 |  | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP/detailed | Deliverable |  | 2002/537, 06/779, 07/0809, 10/082, 23/071, 23/0404 | 20/8/03, 29/11/06, 19/8/09, 26/11/10, withdrawn, minded | 20/8/06, 29/11/09, 19/8/14, 26/11/13 | 290620.68 | 676511.93 | 1.28 | 2002-11-28 | Mainstream (Housing) | 39 |  |  | 39 | GREENFIELD |  | CALIFORNIA
HLA | 590 |  | Landowner | Manse Brae | Avonbridge | Mr W Jeffrey | 0 | 0 | 6 | 6 |  | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed | Deliverable with Constraints | Retrospective planning application to be approved | 008/0081, 22/0603, 25/0259 | 9/7/09, 31/3/23, pending | 9/7/12, 30/3/26 | 290971 | 672909 | 0.35 | 2007-01-11 | Mainstream (Housing) |  | 6 |  | 6 | GREENFIELD |  | AVONBRIDGE
HLA | 589 |  | Private Dev. | Linhouse Farm | Avonbridge | Mixed | 2 | 0 | 2 | 2 |  | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed | Deliverable |  | 06/99, 08/711, 18/23, 23/0489 | 7/3/07, 18/6/09,16/3/18, 19/1/24 | 7/3/12, 18/6/14, 5/3/21, 18/1/27 | 290492.95 | 671278.34 | 0.31 | 2007-01-11 | Mainstream (Housing) |  | 2 |  | 2 | BROWNFIELD |  | AVONBRIDGE
HLA | 586 |  | Private Dev. | Myrehead Farm | Myrehead | Mixed | 2 | 3 | 5 | 8 |  | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed | Deliverable | Individual planning applications to be made. | 07/978, 07/981, 14/98, 17/573, 19/624, 20/049, 20/0205 | 2/4/09, 15/6/10, 11/8/15, 24/11/17, 6/12/19, 31/7/20, 19/6/20 | 2/4/14, 15/6/13, 11/8/18, 23/11/19, 5/12/22, 30/7/23, 18/6/23 | 296548.07 | 677543.74 | 0.59 | 2007-01-11 | Mainstream (Housing) |  | 8 |  | 8 | BROWNFIELD |  | WHITECROSS
HLA | 658 | H28 | Private Dev. | Standburn West | Standburn | A Paterson/D Green | 1 | 0 | 29 | 29 |  | 1 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Deliverable with Constraints | Planning application to be made. Housebuilder to be confirmed. | 07/1118, 08/406, 17/517, 18/0541 | 8/7/08, 29/1/09, refused, 9/10/19 | 8/7/11, 29/1/12. 8/9/22 | 292840.39 | 674637.23 | 6.76 | 2009-12-03 | Mainstream (Housing) | 7 | 22 |  | 29 | GREENFIELD | F/RUR/030 | DRUMBOWIE
Non Contributing HLA | 358 | H27 | Landowner | Main Street | Slamannan | Mr Kelly | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Constrained | Flooding to be addressed. Planning application to be made. Marketability to be evidenced. Housebuilder to be confirmed. |  |  |  | 285070.39 | 673128.02 | 24.28 | 2002-09-26 | Mainstream (Housing) |  |  |  |  | GREENFIELD |  | SLAMANNAN
Non Contributing HLA | 708 | H22 | Landowner | Bridgend Road | Avonbridge | Mr C Miller | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Constrained | Planning application to be made. Housebuilder to be confirmed. |  |  |  | 291280.99 | 672436.25 | 2.85 | 2011-04-27 | Mainstream (Housing) |  |  |  |  | GREENFIELD |  | AVONBRIDGE
Non Contributing HLA | 642 | H25 | Private Dev. | Slamannan Road | Limerigg | Manor Forrest | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Constrained | Planning application to be made. Housebuilder to be confirmed. | 08/617, 12/241, 19/580 | 15/5/09, 28/1/15, refused | 15/5/12, 28/1/18 | 285490.58 | 671101.78 | 1.23 | 2008-09-22 | Mainstream (Housing) |  |  |  |  | BROWNFIELD | F/RUR/031 | LIMERIGG
Non Contributing HLA | 588 |  | Landowner | Carriden Steadings | Muirhouses | Mr & Mrs Tom Barkhouse | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed extant | Constrained | Planning consent to be implemented. | 06/643, 12/812, 16/32 | 29/11/06, 26/4/13, 23/3/16 | 29/11/11, 25/4/16, 22/3/19 | 302355.78 | 680760.37 | 0.58 | 2007-01-11 | Mainstream (Housing) |  |  |  |  | BROWNFIELD |  | GRANGE
Non Contributing HLA | 534 | H24 | Private Dev. | Church Road | California | Mixed | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Constrained | Planning application to be made. Housebuilder to be confirmed. | 13/746, 13/745, 16/0095, 17/137, 18/137 | withdrawn, withdrawn, 7/10/16, withdrawn, 5/2/21 | 6/10/19, 4/2/24 | 291034.83 | 676603.14 | 1.88 | 2005-04-27 | Mainstream (Housing) |  |  |  |  | MIXED |  | CALIFORNIA
Non Contributing HLA | 100 |  | Private Dev. | Church Road 1 | California | Mixed | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed extant | Constrained | Planning consent to be implemented. Housebuilder to be confirmed. | 2001/0686, 2003/687, 2004/569 | 26/02/2003, 29/10/03, 23/11/04 | 26/02/2006, 29/10/08, 23/11/09 | 290788.68 | 676387.75 | 3.82 | 1999-04-01 | Mainstream (Housing) |  |  |  |  | GREENFIELD |  | CALIFORNIA
Non Contributing HLA | 421 |  | Landowner | Station Road 1 | Whitecross | Unknown | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | detailed extant | Undeliverable | Planning consent to be implemented. Housebuilder to be confirmed. | 2003/997, 06/324, 07/882, 08/888 | 28/4/04, refused, refused, 26/6/09 | 28/4/09, 26/6/14 | 297090.61 | 676976.79 | 0.41 | 2004-02-10 | Mainstream (Flats) |  |  |  |  | GREENFIELD |  | WHITECROSS
Non Contributing HLA | 340 | BUS02 | Landowner | Manuel Works | Whitecross | Arrochar Developments Ltd | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | outline | Constrained | Planning consent to be implemented. Housebuilder to be confirmed. | 10/188, 14/0360, 17/792, | refused, withdrawn, 22/7/22 | 21/7/25 | 296227.38 | 677031.11 | 113.88 | 2002-09-13 | Mixed |  |  |  |  | MIXED | F/RUR/029 | WHITECROSS
HLA | 41 |  | Landowner | Slamannan Road North | Avonbridge | Mr G Melville | 0 | 0 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 |  | outline | Deliverable with Constraints | Planning application to be approved followed by detailed application. | P/19/0568/PPP, 24/102 | 1/3/21, pending | 29/2/24, | 290971.68 | 672672.33 | 0.86 | 1999-04-01 | Mainstream (Housing) | 18 |  |  | 18 | GREENFIELD |  | AVONBRIDGE
Non Contributing HLA | 522 | H58 | Landowner | Slamannan Road 1 | Limerigg | Unknown | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | LDP | Deliverable with Constraints | Planning application to be made. Housebuilder to be confirmed. | 18/0693/PPP | 25/9/19 | 24/9/22 | 285705.04 | 671318.45 | 6.28 | 2004-12-21 | Mainstream (Housing) |  |  |  |  | GREENFIELD |  | LIMERIGG
[7 empty] | 700 | 256 | 4712 | 4968 | 2226 | 344 | 459 | 750 | 873 | 643 | 701 | 355 | 261 | 126 | 90 | 366 | [12 empty] | 1144 | 3824
[12 empty] | Long Term 2035+: 4968 | [13 empty] | 4968